## Progress Planning and Tracking
Project Name: | IT Alumni Database
Report Date: | 2018-04-29
[5 empty] | Milestone #1 |  |  |  | Milestone #2 |  |  |  | Milestone #3
Deliverable | Tasks | Complete% | Current Status Memo | Assigned To | 2018-01-28 | 2018-02-04 | 2018-02-11 | 2018-02-18 | 2018-02-25 | 2018-03-04 | 2018-03-11 | 2018-03-18 | 2018-03-25 | 2018-04-01 | 2018-04-08 | 2018-04-15 | 2018-04-22 | 2018-04-29
Complete Database | Choose database enviornment | 0% |  | Zack,Vy,Ricky, Desiree | 2018-01-28: 5
| Install the database server | 0% |  | Zack,Vy,Ricky, Desiree | bar: 2018-01-28
| ERD conceptual design | 0% |  | Vy | 2018-02-04: 5
| Logical design | 0% |  | Desiree | 2018-02-11: 4
| Learning SQL Server | 0% |  | Zack,Vy,Ricky, Desiree | 2018-02-04: 8; 2018-02-11: 8
| Create the database schema (DDL) | 0% |  | Vy | 2018-02-11: 4; 2018-02-18: 4
| Execute the DDL on the database server | 0% |  | Vy | 2018-02-18: 4
| Testing | 0% |  | Zack,Vy,Ricky, Desiree | 2018-02-11: 10; 2018-02-18: 10
Insert Record Scripting | Learning Python | 0% |  | Zack,Vy,Ricky, Desiree | 2018-01-28: 20; 2018-02-04: 12; 2018-02-11: 12; 2018-02-18: 12; 2018-02-25: 8
| Be able to connect to database using Python | 0% |  | Vy | 2018-02-25: 4
| Collect and parse data from excel spreadsheet | 0% |  | Zack | 2018-02-25: 8; 2018-03-04: 8; 2018-03-11: 6
| Create logic to check if record exists in the database | 0% |  | Desiree | 2018-03-04: 6
| Work on logic to insert new record into the database | 0% |  | Ricky | 2018-03-04: 20; 2018-03-11: 20; 2018-03-18: 20
| Test by using existing and new KSU Alumni Accounts | 0% |  | Zack, Vy, Ricky, Desiree | 2018-03-11: 10; 2018-03-18: 10
Update Record Scripting | Research optimal amount of times to use web crawler | 0% |  | Zack,Vy,Ricky, Desiree | 2018-03-25: 5
| Create script that will run web crawler | 0% |  | Zack,Vy,Ricky, Desiree | 2018-03-25: 8; 2018-04-01: 8
| Work on logic to check which items need updating | 0% |  | Zack,Vy,Ricky, Desiree | 2018-03-25: 10; 2018-04-01: 12; 2018-04-08: 10
| Work on logic that will update records automatically | 0% |  | Zack,Vy,Ricky, Desiree | 2018-04-08: 20; 2018-04-15: 20
| Test by making changes to LinkedIn accounts | 0% |  | Zack, Vy, Ricky, Desiree | 2018-04-08: 20; 2018-04-15: 20
Final report | Final report | 0% |  | Zack,Vy,Ricky, Desiree | 2018-04-22: 5; 2018-04-29: 5
| Formal presentation | 0% |  | Zack,Vy,Ricky, Desiree | 2018-04-22: 5; 2018-04-29: 5
| Final report submission | 0% |  | Ricky | 2018-04-22: 5; 2018-04-29: 5
| Total workload | 401 |  |  | 25 | 25 | 38 | 30 | 20 | 34 | 36 | 30 | 23 | 20 | 50 | 40 | 15 | 15
Legend
Planned
Delayed
Number | Workload: man hour